## Sheet1-Control Mapping & Recomm
Asset ID | Asset Name | Asset Owner | Asset Type | Classification | NIST Control Family | Specific Control | Control Status | Evidence Location | Risk Level | Finding/Gap | Recommendation | Responsible Team | Remediation Due Date | Current Status
APP-001 | Payroll Application | HR Team | Application | Confidential | AC - Access Control | AC-2 Account Management | Implemented | SharePoint/Access_Review | Medium | Inactive accounts not reviewed quarterly | Implement quarterly access reviews per AC-2 | IAM Team | 2025-11-01 | In Progress
SRV-002 | HR Server | IT Operations | Server | Internal | SI - System & Info Integrity | SI-2 Flaw Remediation | Partially Implemented | Jira Ticket #3421 | High | Patch management delays beyond 30 days | Automate patch deployment and track via ServiceNow | IT Security Ops | 2025-11-15 | Pending
DB-003 | Customer Database | Database Admin | Database | Highly Confidential | SC - System & Comm Protection | SC-7 Boundary Protection | Implemented | Audit Folder Q3 | Low | Encryption enabled, meets standard | Continue periodic encryption validation | DB Admin Team | N/A | Compliant
FW-004 | Network Firewall | Network Security | Network Device | Internal | CM - Config Management | CM-6 Configuration Settings | Not Implemented | Pending CMDB Update | High | Baseline configuration not documented | Document baseline configuration and review quarterly | Network Team | 2025-11-10 | Open

## Sheet2- Control Assessment & Ev
Control ID | Control Name | Control Family | Evidence Type | Evidence Status | Owner | Risk Level | Recommendation | CSF Function | RMF Phase | Notes
AC-2 | Account Management | Access Control (AC) | Access Review Report | Missing | IT Ops | High | Implement periodic access review for admin accounts | Protect | Assess | No evidence of access review logs
AC-6 | Least Privilege | Access Control (AC) | Role Matrix / RBAC Config | Partial | IAM | High | Enforce least privilege and document RBAC roles | Protect | Implement | Some roles have broad admin rights
AU-2 | Audit Events | Audit & Accountability (AU) | Sentinel Log Screenshot | Present | SecOps | Medium | Ensure log retention for 90 days | Detect | Implement | Logs active but short retention
CM-8 | Information System Component Inventory | Configuration Management (CM) | CMDB Record | Present | Asset Mgmt | Low | Ensure all cloud instances linked to CMDB | Identify | Categorize | Missing 2 finance app records
SI-2 | Flaw Remediation | System & Information Integrity (SI) | Vulnerability Scan | Missing | Vulnerability Mgmt | High | Validate patch status and close open findings | Detect | Assess | Nessus report pending

## Sheet4- Risk Summary & Reportin
Risk Level | ETA / Due Date | Owner / Responsible Team | Notes / Remediation Guidance
High | 2–4 weeks | IT Ops, IAM,Vulnerability Mgmt | Critical issues; remediate quickly to avoid impact on system/data
Medium | 1–2 months | SecOps | Moderate impact; fix in reasonable timeframe
Low | 2–3 months | Asset Mgmt | Minor impact; track for compliance and completeness